Expanded Project Proposal & Execution Plan

Project: LabTrack UM — Local TA Lab Inventory System
Semester Window: January 12 – May 12
Student: Herby K. Hertilien

1. Project Overview (Expanded)

1.1 Purpose of the Project

LabTrack UM is a locally hosted desktop application designed to improve accountability and inventory control for Teaching Assistants managing engineering lab equipment at the University of Miami. The system addresses recurring issues with missing, misplaced, or damaged equipment by providing a centralized database that records item details, storage locations, condition, and check-in/check-out history.

The project will be developed incrementally across the Spring semester, with clearly defined stages to ensure steady progress, measurable outcomes, and regular status reporting.

1.2 Problem Statement

Currently, lab equipment tracking relies on informal or inconsistent methods, leading to:

- Unclear ownership of missing items

- Lack of visibility into item condition

- No reliable history of equipment usage

- Inefficient preparation for lab sessions

This project aims to replace these fragmented processes with a structured, locally run system that is easy for TAs to use during real lab operations.

2. System Scope (What This Project Covers)

2.1 In-Scope Functionality (Version 1)

- Local MySQL database storing all lab equipment records

- Desktop application with graphical interface

- Inventory management (add, update, delete items)

- Equipment status tracking (functional, broken, in repair)

- Physical location tracking (building, room, cabinet/shelf)

- Check-in / check-out logging with timestamps and user identification

- Ability to view:

  - All inventory

  - Currently checked-out items

  - Broken or in-repair items

2.2 Out-of-Scope (Deferred / Future Enhancements)

- Cloud deployment or remote access

- University-wide asset integration

- Advanced analytics or reporting dashboards

- Authentication tied to university login systems

3. Technology Stack

This stack is intentionally conservative to reduce risk and ensure completion within one semester.

3.1 Application Layer

- Language: Java

- GUI Framework: Java Swing

- Development Environment: IntelliJ IDEA or Visual Studio Code

3.2 Data Layer

- Database: MySQL (local instance)

- Database Access: JDBC (Java Database Connectivity)

3.3 Deployment Model

- Application runs locally on lab or TA machines

- Database hosted on localhost or designated lab machine

- No external network or cloud dependencies

4. Development Approach

The project will follow a phased, incremental development approach, where each phase produces tangible, demonstrable results. This structure supports ongoing status reports, instructor check-ins, and risk control.

Each phase answers:

- What was planned?

- What was completed?

- What is next?

5. Project Phases & Timeline (Jan 12 – May 12)

Phase 1 – Project Initialization & Planning

Timeframe: Jan 12 – Jan 26

Objectives:

- Finalize system scope and requirements

- Confirm technology stack

- Establish project structure and repository

Deliverables:

- Approved expanded project proposal

- High-level system architecture outline

- Initial database design draft

- Project folder structure (code + documentation)

Status Report Focus:
“Project setup, requirements clarification, and technical decisions finalized.”

Phase 2 – Database Design & Backend Foundations

Timeframe: Jan 27 – Feb 16

Objectives:

- Design and implement MySQL database schema

- Create core Java model classes

- Establish JDBC connectivity

Work Performed:

- Create tables for items, users, and check-outs

- Test CRUD operations via Java (non-GUI)

- Validate data integrity and relationships

Deliverables:

- Functional local database

- Verified Java ↔ MySQL connection

- Initial data access classes (DAO layer)

Status Report Focus:
“Database schema implemented and backend logic validated.”

Phase 3 – Core Inventory Management Interface

Timeframe: Feb 17 – Mar 9

Objectives:

- Develop Swing-based UI for inventory management

- Connect UI components to backend logic

Work Performed:

- Inventory table display (JTable)

- Add/Edit/Delete item functionality

- Status and location updates

Deliverables:

- Working inventory management screen

- Ability to manage equipment records through GUI

Status Report Focus:
“Core inventory management features implemented and operational.”

Phase 4 – Check-In / Check-Out Functionality

Timeframe: Mar 10 – Mar 30

Objectives:

- Implement equipment usage tracking

- Enforce basic business rules

Work Performed:

- Check-out process (assign item to user with timestamp)

- Check-in process (return item, close record)

- Prevent invalid actions (double checkout, missing returns)

Deliverables:

- Fully functional checkout workflow

- Active checkout and history views

Status Report Focus:
“Equipment tracking and accountability mechanisms completed.”

Phase 5 – Testing, Refinement, and Usability Improvements

Timeframe: Mar 31 – Apr 20

Objectives:

- Improve system reliability and usability

- Perform scenario-based testing

Work Performed:

- Input validation

- UI refinements

- Edge case handling

- Sample data testing

Deliverables:

- Stable application build

- Reduced errors and improved user flow

Status Report Focus:
“System stabilized through testing and refinement.”

Phase 6 – Documentation & Final Delivery

Timeframe: Apr 21 – May 12

Objectives:

- Prepare final deliverables and demonstration

- Document system for handoff

Deliverables:

- User guide for TAs

- Technical documentation (architecture + schema)

- Final system demo

Status Report Focus:
“Project finalized, documented, and ready for evaluation.”